## Sheet1
Task number | Outline number | Name | Assigned to | Start | Finish | Duration | Depends on | % complete | Priority | Bucket | Dependents (after) | Effort | Effort completed | Effort remaining | Milestone | Notes
288 | 1.27.27.6 | (Zack B) DEMO - RM Staging at Shell Road 2026 (ODS) | Rohit Shrivastav | 2026-06-01 09:00 | 2026-06-30 17:00 | 22 days |  | 0% | Medium | Bucket 1 | [5 empty] | Live Public Folders > Michelman Reporting > Production and Shipping > Cogan Excel AD HOC Reports > 6/23 Nick to check to see if have similar report
323 | 1.27.30.1 | (Zack B) Shell and Kemper - 530 Report | Rohit Shrivastav | 2026-06-15 09:00 | 2026-06-30 17:00 | 12 days |  | 0% | Medium | Bucket 1 | [5 empty] | 5/28 - Added based on Eric Beck email forward from Brent 6/23 - Public Folders>Michelman Reporting> Production and Shipping> Contract Manufacturing Orders> Dashboard - CM Overview LIVE
324 | 1.27.30.2 | (Zack B) CM (Brent Planner 3 December 2024) - Sales Orders < 560 (Problem: Not Enough inventory to Ship) | Rohit Shrivastav | 2026-06-15 09:00 | 2026-06-30 17:00 | 12 days |  | 0% | Medium | Bucket 1 | [5 empty] | 5/28 - Added based on Eric Beck email forward from Brent 6/23 - Public Folders>Michelman Reporting> Production and Shipping> Contract Manufacturing Orders> Dashboard - CM Overview LIVE
325 | 1.27.30.3 | (Zack B) CM - Open Sales Orders Live | Rohit Shrivastav | 2026-06-15 09:00 | 2026-06-30 17:00 | 12 days |  | 0% | Medium | Bucket 1 | [5 empty] | 5/28 - Added based on Eric Beck email forward from Brent 6/23 - Public Folders>Michelman Reporting> Production and Shipping> Contract Manufacturing Orders> Dashboard - CM Overview LIVE
326 | 1.27.30.4 | (Zack B) CM - Inventory on Hand | Rohit Shrivastav | 2026-06-15 09:00 | 2026-06-30 17:00 | 12 days |  | 0% | Medium | Bucket 1 | [5 empty] | 5/28 - Added based on Eric Beck email forward from Brent 6/23 - Public Folders>Michelman Reporting> Production and Shipping> Contract Manufacturing Orders> Dashboard - CM Overview LIVE
327 | 1.27.30.5 | (Zack B) CM - PO Live | Rohit Shrivastav | 2026-06-15 09:00 | 2026-06-30 17:00 | 12 days |  | 0% | Medium | Bucket 1 | [5 empty] | 5/28 - Added based on Eric Beck email forward from Brent 6/23 - Public Folders>Michelman Reporting> Production and Shipping> Contract Manufacturing Orders> Dashboard - CM Overview LIVE
329 | 1.27.31.1 | (Zack B) 1 - Ivan SK 2023 | Rohit Shrivastav | 2026-06-22 09:00 | 2026-06-30 17:00 | 7 days |  | 0% | Medium | Bucket 1 | [5 empty] | Added 6/22/26 - Here are the reports Ivan asked to me work on. The 1 – Ivan FC 2023 and 1 – Ivan FC 2023 Forecast are the original reports, the SK variants are the ones I duplicated for him. All of his reports already on our list are in the Cogan Excel AD HOC Reports folder, while these 4 are one folder above it. According to the schedule, the reports were created in March 2026. Public Folders > Michelman Reporting > Production and Shipping
330 | 1.27.31.2 | (Zack B) 1 - Ivan SK 2023 Forecast | Rohit Shrivastav | 2026-06-22 09:00 | 2026-06-30 17:00 | 7 days |  | 0% | Medium | Bucket 1 | [5 empty] | Added 6/22/26 - Here are the reports Ivan asked to me work on. The 1 – Ivan FC 2023 and 1 – Ivan FC 2023 Forecast are the original reports, the SK variants are the ones I duplicated for him. All of his reports already on our list are in the Cogan Excel AD HOC Reports folder, while these 4 are one folder above it. According to the schedule, the reports were created in March 2026. Public Folders > Michelman Reporting > Production and Shipping
331 | 1.27.31.3 | (Zack B) 1 - Ivan FC 2023 | Rohit Shrivastav | 2026-06-23 09:00 | 2026-06-30 17:00 | 6 days |  | 0% | Medium | Bucket 1 | [5 empty] | Added 6/22/26 - Here are the reports Ivan asked to me work on. The 1 – Ivan FC 2023 and 1 – Ivan FC 2023 Forecast are the original reports, the SK variants are the ones I duplicated for him. All of his reports already on our list are in the Cogan Excel AD HOC Reports folder, while these 4 are one folder above it. According to the schedule, the reports were created in March 2026. Public Folders > Michelman Reporting > Production and Shipping
332 | 1.27.31.4 | (Zack B) 1 - Ivan SFC2023 Forecast | Rohit Shrivastav | 2026-06-23 09:00 | 2026-06-30 17:00 | 6 days |  | 0% | Medium | Bucket 1 | [5 empty] | Added 6/22/26 - Here are the reports Ivan asked to me work on. The 1 – Ivan FC 2023 and 1 – Ivan FC 2023 Forecast are the original reports, the SK variants are the ones I duplicated for him. All of his reports already on our list are in the Cogan Excel AD HOC Reports folder, while these 4 are one folder above it. According to the schedule, the reports were created in March 2026. Public Folders > Michelman Reporting > Production and Shipping
178 | 1.22.12 | (Zack/Dave 7/7)BOM WERCS Integrity Check | [13 empty] | 6/2 - Added 6/2. Ticket#2008983 from connectwise to Correct cognos as it isn't working. Recreated in PBI. Public Folders>Michelman Reporting>MDG>BOM's Needs assigned 6/9 assigned to Dave. This was request from Cheryl D.
295 | 1.27.27.13 | (Zack B 7/7) Americas - Open Purchase Orders | [13 empty] | Live Public Folders > Michelman Reporting > Production and Shipping > Cogan Excel AD HOC Reports > 6/16 Nick to check to see if duplicate 7/7 Not a duplicate. Assign to Zach B
283 | 1.27.27.1 | 1 - Ivan LIVE Global Inventory Excel | [13 empty] | Once per day Public Folders > Michelman Reporting > Production and Shipping > Cogan Excel AD HOC Reports > http://cognos/ibmcognos/cgi-bin/cognos.cgi?b_action=cognosViewer&ui.action=run&ui.object=%2fcontent%2ffolder%5b%40name%3d%27Michelman%20Reporting%27%5d%2ffolder%5b%40name%3d%27Production%20and%20Shipping%27%5d%2freport%5b%40name%3d%271%20-%20Ivan%20Global%20Inventory%20Excel%20-%20Select%20Date%27%5d&ui.name=1%20-%20Ivan%20Global%20Inventory%20Excel%20-%20Select%20Date&run.outputFormat=spreadsheetML&run.prompt=true&ui.backURL=%2fibmcognos%2fcgi-bin%2fcognos.cgi%3fb_action%3dxts.run%26m%3dportal%2fcc.xts%26m_folder%3diB952087C935D4F6490A882F625456E48 https://michem.sharepoint.com/:x:/r/sites/SOPandSOE/_layouts/15/Doc.aspx?action=edit&sourcedoc=%7B1801b57b-9775-4ed0-9404-0c22eaed124a%7D&wdExp=TEAMS-TREATMENT&web=1&TeamsCID=62d45496-fc05-44f7-9f69-6be95b84e196 6/24 Nick Notes: 4 pages/3 queries, not as large. Half day +- couple hours 7/7 Nick to see if ODS for possible move to Zach B | Once per day Public Folders > Michelman Reporting > Production and Shipping > Cogan Excel AD HOC Reports > http://cognos/ibmcognos/cgi-bin/cognos.cgi?b_action=cognosViewer&ui.action=run&ui.object=%2fcontent%2ffolder%5b%40name%3d%27Michelman%20Reporting%27%5d%2ffolder%5b%40name%3d%27Production%20and%20Shipping%27%5d%2freport%5b%40name%3d%271%20-%20Ivan%20Global%20Inventory%20Excel%20-%20Select%20Date%27%5d&ui.name=1%20-%20Ivan%20Global%20Inventory%20Excel%20-%20Select%20Date&run.outputFormat=spreadsheetML&run.prompt=true&ui.backURL=%2fibmcognos%2fcgi-bin%2fcognos.cgi%3fb_action%3dxts.run%26m%3dportal%2fcc.xts%26m_folder%3diB952087C935D4F6490A882F625456E48 https://michem.sharepoint.com/:x:/r/sites/SOPandSOE/_layouts/15/Doc.aspx?action=edit&sourcedoc=%7B1801b57b-9775-4ed0-9404-0c22eaed124a%7D&wdExp=TEAMS-TREATMENT&web=1&TeamsCID=62d45496-fc05-44f7-9f69-6be95b84e196 6/24 Nick Notes: 4 pages/3 queries, not as large. Half day +- couple hours 7/7 Nick to see if ODS for possible move to Zach B | Once per day Public Folders > Michelman Reporting > Production and Shipping > Cogan Excel AD HOC Reports > http://cognos/ibmcognos/cgi-bin/cognos.cgi?b_action=cognosViewer&ui.action=run&ui.object=%2fcontent%2ffolder%5b%40name%3d%27Michelman%20Reporting%27%5d%2ffolder%5b%40name%3d%27Production%20and%20Shipping%27%5d%2freport%5b%40name%3d%271%20-%20Ivan%20Global%20Inventory%20Excel%20-%20Select%20Date%27%5d&ui.name=1%20-%20Ivan%20Global%20Inventory%20Excel%20-%20Select%20Date&run.outputFormat=spreadsheetML&run.prompt=true&ui.backURL=%2fibmcognos%2fcgi-bin%2fcognos.cgi%3fb_action%3dxts.run%26m%3dportal%2fcc.xts%26m_folder%3diB952087C935D4F6490A882F625456E48 https://michem.sharepoint.com/:x:/r/sites/SOPandSOE/_layouts/15/Doc.aspx?action=edit&sourcedoc=%7B1801b57b-9775-4ed0-9404-0c22eaed124a%7D&wdExp=TEAMS-TREATMENT&web=1&TeamsCID=62d45496-fc05-44f7-9f69-6be95b84e196 6/24 Nick Notes: 4 pages/3 queries, not as large. Half day +- couple hours 7/7 Nick to see if ODS for possible move to Zach B
284 | 1.27.27.2 | 1 - Ivan Global Inventory Excel - Select Date | [13 empty] | Once per day Public Folders > Michelman Reporting > Production and Shipping > Cogan Excel AD HOC Reports > http://cognos/ibmcognos/cgi-bin/cognos.cgi?b_action=cognosViewer&ui.action=run&ui.object=%2fcontent%2ffolder%5b%40name%3d%27Michelman%20Reporting%27%5d%2ffolder%5b%40name%3d%27Production%20and%20Shipping%27%5d%2freport%5b%40name%3d%271%20-%20Ivan%20Global%20Inventory%20Excel%20-%20Select%20Date%27%5d&ui.name=1%20-%20Ivan%20Global%20Inventory%20Excel%20-%20Select%20Date&run.outputFormat=spreadsheetML&run.prompt=true&ui.backURL=%2fibmcognos%2fcgi-bin%2fcognos.cgi%3fb_action%3dxts.run%26m%3dportal%2fcc.xts%26m_folder%3diB952087C935D4F6490A882F625456E48 https://michem.sharepoint.com/:x:/r/sites/SOPandSOE/_layouts/15/Doc.aspx?action=edit&sourcedoc=%7B1801b57b-9775-4ed0-9404-0c22eaed124a%7D&wdExp=TEAMS-TREATMENT&web=1&TeamsCID=62d45496-fc05-44f7-9f69-6be95b84e196 6/24 Nick Notes: 4 pages/3 queries, not as large. Half day +- couple hours 7/7 Nick to see if ODS for possible move to Zach B